## Sheet1
Requirements Traceability Matrix
Project Name: |  | Contact List App |  | Document Author: |  | QA Team
Requirement ID / CONTACT LIST DOCUMENTATION ID | Requirement Name / Description | Requested / Approved By: | Scope Deliverable or Feature | Scope ID | User Story or Work Package | Assigned To | Test Case | Current Status | Bug ID
Req - 01 / Contacts - 1 | POST / Add Contact | Product Owner | Contact Creation | Scope - 1.1 | As a user, I want to create new contacts with valid data to expand my contact list | Ahmed Abdallatif | TC - 001 to TC - 031 | Failed | Bug - 001 / Bug - 002 / Bug - 003 / Bug - 004 / Bug - 005 / Bug - 006
Req - 02 / Contacts - 2 | GET / Get Contact List | Product Owner | Contact Retrieval | Scope - 1.2 | As a user, I want to retrieve all contacts to view my complete contact list | Aya Abu Ali | TC - 032 to TC - 039 | Failed | Bug - 007
Req - 03 / Contacts - 3 | GET / Get Contact | Product Owner | Contact Details | Scope - 1.3 | As a user, I want to fetch a specific contact's details by ID for focused viewing | Aya Abu Ali | TC - 040 to TC - 044 | Failed | Bug - 008
Req - 04 / Contacts - 4 | PUT / Update Contact | Product Owner | Contact Replacement | Scope - 1.4 | As a user, I want to fully replace contact records to correct major changes | Ahmed Abdallatif | TC - 045 to TC - 074 | Failed | Bug - 009 / Bug - 010 / Bug - 011 / Bug - 012 / Bug - 013 / Bug - 014
Req - 05 / Contacts - 5 | PATCH / Update Contact | Product Owner | Contact Update | Scope - 1.5 | As a user, I want to partially update contact details to keep records current | Aya Abu Ali | TC - 075 to TC - 102 | Failed | Bug - 015
Req - 06 / Contacts - 6 | DELETE / Delete Contact | Product Owner | Contact Removal | Scope - 1.6 | As a user, I want to delete obsolete contacts to maintain list relevance | Ahmed Abdallatif | TC - 103 to TC - 117 | Failed | Bug - 016 / Bug - 017 / Bug - 018 / Bug - 019 / Bug - 020
Req - 07 / Users - 1 | POST / Add User | Product Owner | User Registration | Scope - 2.1 | As a new user, I want to create an account to access the contact list | Mesk Alrayyes | TC - 118 to TC - 129 | Failed | Bug - 027 / Bug - 028
Req - 08 / Users - 2 | GET / Get User Profile | Product Owner | Profile Retrieval | Scope - 2.2 | As a user, I want to view my profile details to verify account information | Mesk Alrayyes | TC - 130 to TC - 135 | Failed | Bug - 021 / Bug - 022 / Bug - 023
Req - 09 / Users - 3 | PATCH / Update User | Product Owner | Profile Update | Scope - 2.3 | As a user, I want to update my profile to keep information accurate | Mesk Alrayyes | TC - 136 to TC - 145 | Passed | -
Req - 10 / Users - 4 | POST / Log Out User | Product Owner | Session Management | Scope - 2.4 | As a user, I want to log out securely to protect my account | Lina Shaqoura | TC - 146 to TC - 154 | Passed | -
Req - 11 / Users - 5 | POST / Log In User | Product Owner | Authentication | Scope - 2.5 | As a registered user, I want to log in to access my contact list | Lina Shaqoura | TC - 155 to TC - 163 | Failed | Bug - 024
Req - 12 / Users - 6 | DELETE / Delete User | Product Owner | Account Deletion | Scope - 2.6 | As a user, I want to delete my account to remove all personal data | Lina Shaqoura | TC - 164 to TC - 172 | Failed | Bug - 025 / Bug - 026 / Bug - 027 / Bug - 028
Assigned To
Ahmed Abdallatif
Aya Abu Ali
Mesk Alrayyes
Lina Shaqoura
Current Staus
Passed
Failed